## Pillars-Goals
Neighborhood Network Pillars & Goals
Pillars | Objective | Elements | Network Goal
Infrastructure | Network has the right support systems in place to move the work forward and an understanding of how much it will cost to maintain the backbone functions of the Network. | Governance, Backbone, Data/Evaluation/Improvement, Network Collaboration, Policy & Advocacy | The financial overall financial goal is to raise$900K over the course of three years. The purpose of this goal is to support the various community initiatives as well as grow the BIRNN organization through hiring staff.
Programming | Network is serving families holistically through targeted initiatives and high quality programs and that are integrated across partners. | Education, Health, Safety Net, Workforce, Safe Communities | Develop/Growth organization to support the increased needs of the community by adding employees, an Executive Director, and opening a new office space. The purpose of this goal is to establish a organization equipped to become an independent network. Increase the capabilities of other organizations associated with the network by offering training and funding opportunities. The purpose of this goal is to build stronger community networks through collaboration.
Community Initiatives | Network is developing to address constraints hindering achievement of the growth potential from systemic perspective. | Capital, Labor, Transportation, Land/Infrastructure, Technology/Management Information | Enhance the experience and effectiveness of the services and programming within the networks so that the community members are equipped to change their lives. The purpose of this goal is to provide high quality services that the community wants and needs.
Sustainability | Networks have a plan for long-term success, including generating funds, establishing a succession plan, and ensuring equitable use of resources to meet essential needs of the neighborhood (both present and future). | Fundraising, Human Development, Quality of Life | Improve community engagement to develop leaders and civic partnership and influence to be included in community’s decisions. The purpose of this goal is to incorporate the community leaders in the activities of the network and to also be a thought partner to the civic decisions that are made.
Community Engagement | Network is purposeful, equitable, and transparent so that community members are true partners for achieving impact. | Engagement Philosophy, Equity, Visibility, Effectively Integrating Community Voice | Obtain business investment within the community to support area needs (access to healthy lifestyle opportunities, job opportunities, etc.) including a grocery store and business influx. The purpose of this goal is to grow the financial stability of the communities that are being served.

## Infrastructure
Neighborhood Network Action Plan
Infrastructure | Goal: Strengthen BIRNN’s infrastructure by creating a simple, capacity-building review system with staff, the steering committee, and community reps that regularly tracks progress and supports continuous improvement.
| Action Step 1. We will hold quarterly meetings with staff, the RAC, and the steering committee to review the workplan and progress, track progress, and make any needed adjustments. | Action Step 2. We will create a simple, regular review process with staff, the steering committee, subcommittee chairs, and RAC chairs to look at how we share information with the broader community, see what’s working, capture lessons learned, and improve updates that guide future planning and resource decisions. Add process into NN roll charter (expansion of charter). | Action Step 3. Strengthen BIRNN Systems (We will develop and document simple tools, process templates, checklists, shared folders, and train staff and leaders to use them, ensuring BIRNN’s workplan, resources, and communications stay strong and consistent even when people or roles change).
Activity | Each quarter, hold a 60–90 minute meeting with staff, RAC, and the steering committee to: Send a one-page scorecard and agenda 48 hours before the meeting. Review 5–7 key metrics (programs, partnerships, and progress) and identify what’s on track/off track. Agree on up to 3 fixes, each with a clear owner and due date, and send simple notes out within 48 hours. | Activity 1: Quarterly Communication Check-In Every quarter, staff, steering committee, subcommittee chairs, and RAC chairs review a one-page update (key programs, wins, challenges, upcoming events) and send a short recap (email, newsletter, or flyer) to the community. Activity 2: Monthly Community Info Share Once a month, share 1–2 key updates with the broader community (for example: a short email, social media post, flyer, or announcement at partner sites) using the same simple template, so residents hear about progress and resources in real time, not just quarterly. | BIRNN will strengthen its systems by creating a shared online toolkit with simple templates (meeting agenda, notes, scorecard, resource tracker, outreach flyer) so everyone uses the same tools, providing a brief orientation for staff, steering, subcommittee chairs, and RAC chairs on how to use the toolkit, and holding a 60-minute annual “systems tune-up” with staff and key leaders to fix anything confusing and update tools as needed.
Resources | United Way Funding Support | United Way Funding Support | United Way Funding Support
Assignment | Steering Committee, RAC, Subcommittees | BIRNN Staff, Steering Commitee, RAC, Sub-Committee Chairs | BIRNN Staff, Steering Commitee, RAC, Sub-Committee Chairs
Completion Date | Q1 Q2 Q3 Q4 | Q1 Q2 Q3 Q4 | Q1 Q2 Q3 Q4
Priority Ranking | 1 | 1 | 1
Improvement | BIRNN’s infrastructure will be strengthened by a consistent quarterly review system where staff, RAC, and the steering committee use a shared scorecard to see what’s on track or behind, name top issues and turn them into clear action items with owners and dates, and align resources with the workplan and community needs. | Because of this review and communication system, BIRNN will: Have a clear, consistent way to share information with staff, RAC, and community (simple templates, regular updates). Improve internal coordination, because staff, steering, subcommittee chairs, and RAC chairs see the same key updates and next steps. Strengthen decision-making, using lessons learned from quarterly check-ins and monthly updates to guide future plans and resources. Build long-term infrastructure, with a basic system in place (regular reviews + shared tools) that can be used and improved year after year. | These activities will give BIRNN clear, consistent tools that everyone uses, help staff and leaders follow simple written systems, and keep work running smoothly even when roles change, because core processes are documented and shared across the team, making BIRNN’s infrastructure more stable, organized, and easier to plan, report, and improve over time.
Updates | During our March meetings, we will review the workplan with the Steering Committee and RAC using a consistent quarterly review process. We will send a one-page scorecard and agenda at least 48 hours before each meeting, review 5–7 key metrics related to programs, partnerships, and progress, and identify what is on track and what needs attention. At the end of the meeting, we will agree on up to three priority fixes, assign a clear owner and due date for each, and send out brief meeting notes within 48 hours. This quarterly review system will strengthen BIRNN’s infrastructure by keeping everyone aligned, improving follow-through, and ensuring resource decisions stay connected to the workplan and community needs. | I have drafted a simple, regular review process for staff, the Steering Committee, Subcommittee Chairs, and RAC Chairs to assess how we share information with the broader community. The process is designed to identify what’s working, capture lessons learned, and strengthen updates that support future planning and resource decisions. Next, I will share the draft with the Steering Committee and RAC for input, and we will engage each committee during our March meetings while reviewing the workplan. This process will also be added to the NN roll charter as an expansion of the charter. | A draft BIRNN Shared Toolkit will be prepared and ready for review the second week of March. The toolkit outline includes: Toolkit Home (Read Me): purpose, who uses it, and basic how-to instructions Meeting Tools: agenda template, notes template, attendance sheet, action item tracker Quarterly Review Tools: one-page scorecard template, quarterly agenda, follow-up notes template Workplan & Reporting Tools: workplan update template, committee update template, lessons learned template Resource Planning Tools: resource tracker, resource alignment check, purchase/request checklist Outreach & Communications Tools: outreach flyer template, community update template Quick Checklists: pre-meeting (48-hour send), meeting day, post-meeting (48-hour notes), quarterly review checklist
| BIRNN committees have continued reviewing the action plan with all committees as part of ongoing efforts to monitor progress, maintain alignment with the work plan and resources, and identify any needed adjustments. To support a more structured and consistent quarterly review process, Ken has developed a standardized form to be used with each committee to document its review of the action plan, capture key feedback, and record any recommendations or follow-up items. The form will be shared with each committee and used during the next round of action plan reviews to strengthen documentation, accountability, and communication across the network. | BIRNN has made steady progress this quarter in strengthening its internal review and communication system. Through ongoing workplan discussions with staff and committees, we have continued to build a more regular process for reviewing key updates, identifying lessons learned, and improving how information is shared with the broader community. This work supports stronger coordination among staff, the Steering Committee, Subcommittee Chairs, and RAC Chairs by creating greater consistency in the information reviewed and communicated. We are also developing simple tools and templates to support quarterly communication check-ins and monthly community information sharing. These steps are helping to build a stronger foundation for future planning, more informed resource decisions, and long-term communication infrastructure across the network. This review and communication process will also be incorporated into the NN roll charter as part of the charter expansion. | BIRNN has continued making progress on Action Step 3 by moving from toolkit planning into tool development and system building. This quarter, core templates and fillable forms were created to support more consistent meetings, quarterly reviews, workplan updates, resource alignment, community communications, and annual systems review. These tools are being organized as a shared toolkit so staff, the Steering Committee, Subcommittee Chairs, and RAC Chairs can use the same formats and expectations across the network. In addition, a brief orientation guide and annual systems tune-up form were developed to help users understand the toolkit, identify anything confusing, and make updates as needed. Together, these steps are helping BIRNN build a more stable, documented, and reusable infrastructure that supports continuity, accountability, and stronger planning even when staff or leadership roles change.
| Progress Update as of 6/18/26: BIRNN has continued to make progress on Action Step 1 by reviewing the action plan with committees as part of ongoing efforts to monitor progress, maintain alignment with the workplan and progress, and identify any needed adjustments. During the March meetings, the workplan was reviewed with the Steering Committee and RAC using the quarterly review process. This included discussion around what is on track, what may need additional attention, and how committee feedback can help guide next steps. To strengthen this process, Ken developed a standardized committee review form to be used with each BIRNN committee. The form is designed to document each committee’s review of the action plan, capture key feedback, and record recommendations or follow-up items. This will help create a more consistent process across committees and improve documentation, accountability, and communication. The form Ken developed will be reviewed by the committees during the August meetings and will begin to be used in Quarter Four. This will help ensure that staff, RAC, the Steering Committee, and BIRNN committees continue to use a shared process to review progress, identify priorities, assign follow-up items, and keep the workplan and progress connected to community needs. | Progress Update as of 6/18/26: BIRNN has continued to make progress on Action Step 2 by strengthening the process for how staff, the Steering Committee, Subcommittee Chairs, and RAC Chairs review and share information with the broader community. The goal of this process is to create a clear and consistent way to review key programs, wins, challenges, upcoming events, and lessons learned so that updates can better support future planning and resource decisions. Ken has created a simple communication review form to support this process. The form will help guide quarterly communication check-ins and monthly community information sharing by documenting key updates, wins, challenges, lessons learned, and follow-up items. The form will be shared with the committees during the August meetings for review and input and will be placed in a newly created forms folder for future use. This work will help improve internal coordination by making sure staff, the Steering Committee, Subcommittee Chairs, and RAC Chairs are reviewing the same key information and next steps. It will also support stronger community communication by helping BIRNN share progress, resources, and upcoming opportunities in a more organized and consistent way. The review and communication process will also be added to the NN roll charter as part of the charter expansion. This will help strengthen BIRNN’s long-term infrastructure by creating a regular system for communication, review, shared learning, and future planning. | Progress Update as of 6/18/26: BIRNN has continued making progress on Action Step 3 by moving from toolkit planning into tool development and system building. This work is focused on creating simple tools, process templates, checklists, and shared folders that will help keep BIRNN’s workplan, resources, meetings, and communications consistent across staff, committees, and leadership groups. Ken has created several core tools and checklists to support this process, including meeting tools, quarterly review tools, workplan update forms, communication review forms, and follow-up templates. These tools are being organized into a BIRNN Shared Toolkit so staff, the Steering Committee, Subcommittee Chairs, and RAC Chairs can use the same formats and follow the same expectations across the network. The toolkit will include a Read Me section, meeting agenda and notes templates, attendance sheets, action item trackers, quarterly review scorecards, workplan and reporting templates, resource planning tools, outreach and communication templates, and quick checklists for before, during, and after meetings. These tools will help strengthen documentation, accountability, and follow-through. The shared toolkit and related forms will be placed in a newly created forms folder for future use. Ken has also created tools that will support orientation and annual systems review so staff and leaders can understand how to use the toolkit, identify anything confusing, and update tools as needed. These steps are helping BIRNN build a more stable, organized, and reusable infrastructure. By documenting core processes and keeping shared tools in one place, BIRNN will be better able to maintain consistency, support transitions when roles change, and improve planning, reporting, communication, and resource decisions over time.
Note on D5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: For the activity, is the Monthly Community Share the Newsletter that currently exists?

## Sustainability
Neighborhood Network Action Plan
Sustainability | Goal: Strengthen BIRNN’s sustainability by building strong, long-term relationships with donors who invest in financial literacy, leadership development, health and wellness, and the overall sustainability of the BIRNN network.
| Action Step 1. Work with staff, partner organizations, and community members to create a simple annual fund development plan that builds a small local donor base, includes at least one community giving event, and tracks a short list of grants and partner contributions to support BIRNN’s key focus areas, including food insecurity, youth development, and workforce development. | Action Step 2. Identify and engage major corporate and philanthropic donors and funders who are invested in Blue Island and Robbins to secure funding for BIRNN’s key focus areas, including food insecurity, youth development, and workforce development. | Action Step 3. Work with the steering committee and RAC to create a simple 2–3 year sustainability plan for BIRNN that maps out expected funding (grants, local donors, in-kind support) and identifies opportunities for joint funding, so the network is not relying on just one source. | Action Step 4. Work with our quarterback agency, Metropolitan Family Services (MFS), to develop a simple, shared data system that tracks participation, outcomes, and partner activities each quarter, so BIRNN can tell its story clearly, support funding requests, and make data-informed decisions. | Action Step 5. Develop and carry out a simple annual recruitment plan to add new steering committee members from Blue Island and Robbins, focusing on residents, youth/parent leaders, and key sectors (education, health, business, faith), so the committee stays representative, active, and aligned with BIRNN’s focus areas.
Activity | BIRNN will bring staff, partner organizations, and a few community members together to draft a simple annual fund plan. This will include making a basic list of local donors and businesses to approach, key grants and partner contributions to track, and an easy spreadsheet or tracker to record who was asked, what was given, and when to follow up. We will also co-create one community giving event each year (for example, a small fundraiser, celebration, or community night) that raises funds and tells the story of BIRNN’s impact. Partners and residents will help pick the theme, date, and location, spread the word with flyers and social media, and thank donors after the event so we can build relationships that support BIRNN’s long-term sustainability. | Q1 – Find & Log Donor Prospects Collect contact info (name, org, email, interest area: food, youth, workforce) at events and meetings, and enter it into a simple spreadsheet within one week. Send a brief thank-you email with a short “What BIRNN Does” overview. Q2 – Connect Donors to Impact Invite interested prospects to a coffee chat or short site visit focused on one area (food insecurity, youth development, or workforce). Share a one-page impact brief and note a clear next step for each person. Q3 – Deepen Engagement Host a small tour or roundtable featuring a resident or partner story from one focus area and include a short “how to fund/partner with BIRNN” segment. Follow up with a simple menu of giving or sponsorship options. Q4 – Secure Commitments & Plan Stewardship Meet with top prospects to discuss specific funding opportunities and share a basic proposal or MOU. Confirm how BIRNN will report back (updates, visits, recognition) and send a short year-end impact recap. | The BIRNN will hold a short annual “sustainability session” with the steering committee and RAC to map out expected funding for the next 2–3 years (key grants, local donors, in-kind support) and list any joint funding opportunities they want to explore together. During this session, they will also agree on 3–5 simple priorities to keep BIRNN stable (for example: renew a key grant, add one new local donor, or secure in-kind space or services). BIRNN will keep this plan in a simple one-page tracker that notes amounts, deadlines, and who is responsible. Twice a year, the steering committee and RAC will do a quick check-in on the plan to update what has been secured, what is pending, and what new opportunities have come up, so sustainability stays on the radar without being overwhelming. | Create a shared template with MFS (Excel or simple form) to track basics: event name, date, location, # of participants, age group, and partners involved. Pick 3–5 common measures for all BIRNN programs (e.g., attendance, zip code, focus area like youth/food/workforce, and 1–2 short feedback questions). Have staff and partners submit data quarterly to MFS using the same template, instead of separate formats. Hold a short quarterly “data huddle” with MFS and BIRNN staff to review what the numbers show, note gaps, and capture 2–3 key stories or highlights. Save one simple quarterly summary page (charts + bullets) that BIRNN can reuse for reports, funders, and the workplan. | Create a Steering Committee Recruitment Plan (with current members): Work with existing steering committee members to list the types of new members needed (residents, parents, youth, education, health, business, faith, etc.), set a target number to recruit each year, and decide how to invite them (referrals, events, direct outreach). Develop Onboarding Materials: Create a short welcome packet with a one-page overview of BIRNN, steering committee roles and expectations, meeting schedule, and key focus areas (youth, food, workforce), plus a simple interest form and contact sheet. Ask current members to review and refine it. Annual Outreach & Selection (guided by current members): Share opportunities at BIRNN events, through partners, and via email/social media; use referrals from current members, hold quick conversations or screenings, and confirm new members together. Orientation Session: Host a brief orientation (in person or on Zoom) where current steering committee members help welcome new members, walk through the packet, answer questions, and connect them to existing work.
Resources | United Way Funding Support | United Way Funding Support | United Way Funding Support
Assignment | BIRNN Staff, Steering Commitee, RAC, Partner Organizations, Blue Island-Robbins Community Members | BIRNN Staff, RAC, Steering Commitee, Partner Orgs (Hope Center, Robbins Park District, Blue Cap, Robbins Library, etc) | BIRNN Staff, RAC, Steering Committee | MSF, BIRNN | BIRNN Program Manager, Steering Committee, RAC
Completion Date | Q1 Q2 Q3 Q4 | Q1 Q2 Q3 Q4 | Q3 Q4 | Q1 Q2 Q3 Q4 | Q1 Q2 Q3 Q4
Priority Ranking | 1 | 1 | 1 | 1 | 1
Improvement | Over time, BIRNN will become more financially stable by having a simple, repeatable fund development system, a growing base of local donors and partners, and an annual community giving event that builds relationships and brings in consistent support to sustain the network’s work in Blue Island and Robbins. | Within one year, BIRNN will have a simple, repeatable donor pipeline that supports long-term sustainability. We will regularly add new qualified donor prospects, move them from first contact to intro meetings and clear next steps, and advance them to proposals and formal commitments that fund key areas like food insecurity, youth development, and workforce development. Each year, BIRNN will secure at least one new funding commitment and one signed MOU, with a basic stewardship plan (updates, visits, and recognition) for every new funder. This growing base of committed donors and partners will help stabilize and sustain the BIRNN network over time. | This action step will give BIRNN a clear, shared sustainability roadmap so the network is not guessing year to year. By planning funding with the steering committee and RAC and checking in on it twice a year, BIRNN will have a simple way to see what money is coming in, what still needs to be secured, and where joint opportunities exist, making the network more stable, less dependent on any single source, and better prepared for the future. | BIRNN and MFS will set up a shared data system (such as REDCap, Excel, or Google Forms/Sheets) with one standard template that staff and partners use each quarter to enter core information: event name, date, focus area (youth, food, workforce, etc.), number of participants, basic demographics, and simple feedback. From this, we will produce 1-page quarterly data summaries (with key numbers, small charts, and 2–3 highlights), brief “data huddle” notes with insights and next steps, and an annual data snapshot for funders and the workplan. These deliverables will give BIRNN a clear, consistent way to collect, store, and review data across the network, reduce time spent chasing numbers, and make it easier to tell our story with solid evidence and real examples. Over time, this stronger data infrastructure will help us spot trends and gaps, improve planning and equity, and strengthen BIRNN’s long-term sustainability and competitiveness for grants and investments. | These activities will give BIRNN a stronger, more sustainable steering committee that better reflects Blue Island and Robbins. Over time, the committee will have clearer roles, smoother onboarding, and steady renewal of members, including residents and leaders from education, health, business, faith, and other sectors, bringing diverse expertise to our work. This will improve participation, continuity, and decision-making, and help keep BIRNN’s priorities closely aligned with community needs.
Updates |  | I will be reaching out to Mariela and our United Way partner to explore connections to corporate partners who may be interested in supporting work in the south suburbs, especially in Blue Island and Robbins. Once we identify potential leads, we will use this information to invite prospective funders to participate in a community tour where they can see BIRNN’s work firsthand, meet our partners, and learn more about funding opportunities tied to our key focus areas—food insecurity, youth development, and workforce development. | Action Step 3 – Sustainability Plan (Update + April Plan) BIRNN will work with the Steering Committee and RAC to develop a simple 2–3 year sustainability plan that maps expected funding (grants, local donors, in-kind support) and identifies joint funding opportunities so the network is not dependent on one source. We will create a one-page sustainability tracker to document projected amounts, deadlines, and responsible leads, and we will use it for twice-yearly check-ins to track what has been secured, what is pending, and what new opportunities have emerged. Plan to meet with the collective committees in April: April: Hold a Sustainability Working Session with the Steering Committee and RAC to (1) list expected funding for the next 2–3 years, (2) identify potential joint funding opportunities, and (3) agree on 3–5 sustainability priorities for the year (e.g., renew a key grant, add a local donor, secure in-kind support). Late April: Meet with the collective committees to share the draft one-page tracker, gather input on funding leads and partnership opportunities, and confirm who will own priority actions and deadlines. Follow-up: Schedule the two annual sustainability check-ins to update the tracker and keep sustainability planning active and manageable. | This action step has not been started yet, but I have reached out to the Metropolitan Family Services (MFS) data team to request insight on improved ways to collect and report BIRNN data. Currently, we use REDCap, but it has limitations for what we need, so we are exploring other solutions that would allow us to better track participation, outcomes, and partner activities each quarter. The goal is to move toward a simple shared data system that helps BIRNN tell its story clearly, strengthen funding requests, and support data-informed decision-making. | BIRNN will launch a simple annual recruitment process to add new Steering Committee members from Blue Island and Robbins, with a focus on residents, youth/parent leaders, and key sectors (education, health, business, and faith). This process will help keep the committee representative, active, and aligned with BIRNN’s focus areas. Plan (how this will be done): Set recruitment needs and targets (with current members): Identify the types of members needed, set an annual recruitment target, and agree on outreach methods (member referrals, events, direct outreach, partner connections). Create onboarding materials: Develop a short welcome packet (BIRNN overview, roles/expectations, meeting schedule, focus areas) plus a simple interest form and contact sheet; have current members review and refine. Outreach and selection: Promote opportunities at BIRNN events and through partners/email/social media, collect referrals, hold brief check-in conversations with interested candidates, and confirm selections with current Steering members. Orientation and welcome: Host a short orientation (in person or Zoom) led by current Steering members to review the packet, answer questions, and connect new members to committees and upcoming meetings.
| Progress Update as of 6/18/26: BIRNN has made progress on this action step by beginning the development of a simple annual fund development plan that will support the network’s key focus areas, including food insecurity, youth development, and workforce development. The plan is being designed to help BIRNN build a small local donor base, identify businesses and community partners to approach, track grant opportunities, and document partner contributions. Ken has created initial tools to support this process, including a donor and business contact list, a grant and partner contribution tracker, and a follow-up spreadsheet to help document who was contacted, what was requested, what was received, and when follow-up is needed. These tools will help create a more organized and repeatable fund development system for BIRNN. The fund development plan and related tools have not yet been reviewed by staff, partners, RAC, or community members. They will be shared during the August meetings for input and feedback. This will allow staff, partner organizations, and community members to help strengthen the plan and ensure that it reflects BIRNN’s priorities and community needs. Sara and Ken are also working on a potential fundraiser as part of BIRNN’s community giving efforts. Additional details about the fundraiser will be shared in the next update. These steps are helping BIRNN build a stronger foundation for long-term sustainability by creating a clear process for tracking local donors, grants, partner contributions, and fundraising opportunities that support the work in Blue Island and Robbins. | Progress Update as of 6/18/26: This quarter, BIRNN has made progress in building its donor and funder pipeline to support the network’s key focus areas, including food insecurity, youth development, and workforce development. Ken has had two meetings with Eric Thompson of Wintrust, and Wintrust will participate as a vendor at the 2026 Safe Summer event. This connection helps strengthen BIRNN’s relationship with potential corporate partners and creates another opportunity for partners to see and support the work happening in Blue Island and Robbins. BIRNN also worked with the grants team to submit a grant application to the Woods Fund. In addition, BIRNN is currently working with the Robbins Park District to explore a new collaborative grant opportunity. This supports our growing approach of pursuing partner-led and collaborative grant submissions, which may be more competitive and better aligned with shared community priorities. Ken has also created a form to track donor, funder, grant, and partner contribution opportunities. This tracking process will help BIRNN document who has been contacted, what opportunities are being explored, what follow-up is needed, and how each opportunity connects to BIRNN’s funding priorities. Ken also spoke with Mariela about shared donors and learned that BIRNN may receive additional insight on storytelling, which can assist with future fundraising efforts. Ken will also be reaching out to Mariela and our United Way partner to explore connections to corporate partners who may be interested in supporting work in the south suburbs, especially in Blue Island and Robbins. Once potential leads are identified, BIRNN will use this information to invite prospective funders to participate in a community tour where they can see BIRNN’s work firsthand, meet partners, and learn more about funding opportunities connected to food insecurity, youth development, and workforce development. These efforts are helping BIRNN build a more organized and sustainable funding pipeline for long-term support. | Progress Update as of 6/18/26: BIRNN has started developing its 2–3 year sustainability plan to help the network map expected funding, identify local donor opportunities, track in-kind support, and explore joint funding possibilities with partners. This work is connected to BIRNN’s broader effort to become less dependent on one funding source and build a more stable funding base to support key focus areas, including food insecurity, youth development, and workforce development. The sustainability working session that was originally planned for April has been postponed to August and will now take place as part of the new workplanning process. During the August meetings, BIRNN will review the draft sustainability plan and one-page sustainability tracker with the Steering Committee and RAC for input. This will help identify expected funding, possible gaps, and shared opportunities for the next 2–3 years. Ken has created a one-page sustainability tracker to begin documenting potential funders, grants, local donors, partner contributions, in-kind support, deadlines, follow-up needs, and responsible leads. The tracker has not yet been placed in a shared folder, but it will be shared during the August meetings as part of the sustainability planning discussion. BIRNN has also continued building its donor and funder pipeline. Ken has had two meetings with Eric Thompson of Wintrust, and Wintrust will participate as a vendor at the 2026 Safe Summer event. BIRNN also worked with the grants team to submit a grant application to the Woods Fund and is currently exploring a new collaborative grant opportunity with the Robbins Park District. These efforts support a stronger approach to partner-led and collaborative funding opportunities. Ken also spoke with Mariela about shared donors and learned that BIRNN may receive additional insight on storytelling, which can support future fundraising efforts. Ken will also reach out to Mariela and our United Way partner to explore connections to corporate partners who may be interested in supporting work in the south suburbs, especially in Blue Island and Robbins. As part of this sustainability work, BIRNN will also begin working on a small fundraising group of three people to help support donor outreach, fundraising planning, and follow-up. Possible sustainability priorities include renewing key grants, adding new local donors, securing in-kind support, strengthening corporate partner relationships, and pursuing joint funding opportunities with partners. These steps are helping BIRNN create a clearer sustainability roadmap so the network can track what has been secured, what is pending, and what still needs follow-up. Over time, this will help BIRNN become more organized, less dependent on any single funding source, and better prepared to sustain its work in Blue Island and Robbins. | Progress Update as of 6/18/26: BIRNN has started progress on Action Step 4 by beginning conversations around how to strengthen the network’s data collection, reporting, and storytelling systems. Ken has reached out to the Metropolitan Family Services data team to request insight on improved ways to collect, organize, and report BIRNN data. We are currently waiting for a response and guidance from the MFS data team. At this time, BIRNN continues to use REDCap as its current data collection system. However, we have identified some limitations with REDCap based on what BIRNN needs for tracking participation, outcomes, partner activities, and quarterly reporting. Because of this, BIRNN is exploring whether REDCap can be improved for our needs or whether another simple shared tool, such as Excel, Google Forms, or Google Sheets, may better support the work. BIRNN has also identified initial common measures that should be tracked across programs and partner activities. These include event name, date, location, number of participants, age group, zip code, focus area such as youth development, food insecurity, or workforce development, partners involved, and short feedback questions. These measures will help create a more consistent way to collect and compare data across BIRNN activities. The quarterly data huddle process will begin in August as part of the new workplanning process. This will allow BIRNN staff and MFS to review what the data shows, identify gaps, capture key stories or highlights, and discuss next steps. The goal is to create a simple quarterly data summary that can be used for reports, funders, storytelling, workplan updates, and data-informed decisions. These steps will help BIRNN move toward a stronger shared data system that makes it easier to tell the network’s story with both numbers and real examples. Over time, this will support stronger planning, better reporting, improved funding requests, and more informed decisions across BIRNN’s work in Blue Island and Robbins. | Progress Update as of 6/18/26: BIRNN has started progress on Action Step 5 by developing a simple annual recruitment process to add new Steering Committee members from Blue Island and Robbins. This process is focused on helping the Steering Committee remain representative, active, and connected to BIRNN’s key focus areas, including food insecurity, youth development, and workforce development. Ken has created initial recruitment tools to support this process, including materials that can help identify potential members, collect interest, track contacts, and support onboarding. These tools will help BIRNN create a more consistent process for recruiting, welcoming, and orienting new Steering Committee members. The recruitment plan will be shared with the current Steering Committee during the August meetings for review and input. BIRNN’s annual target will be to recruit three new Steering Committee members, with a focus on residents, parent and youth leaders, and key sectors such as business, education, health, and faith. At this time, BIRNN is placing special focus on strengthening representation from the business community, while also identifying potential members from the education sector. Some potential new members have already been identified from the business and education communities. After the recruitment plan is reviewed, BIRNN will continue outreach through partner referrals, community events, direct outreach, and existing relationships in Blue Island and Robbins. Once new members are identified and confirmed, BIRNN will begin an orientation process to welcome them, review the Steering Committee role and expectations, explain BIRNN’s focus areas, and connect them to current committees and upcoming work. These steps will help strengthen participation, continuity, and decision-making while keeping BIRNN’s leadership connected to community needs.

## Community Engagement
Neighborhood Network Action Plan
Community Engagement | Goal: Build inclusive, consistent spaces where residents and partners lead and shape BIRNN’s work.
| Action Step 1: Launch a quarterly community engagement and advocacy plan where residents, partners, and the RAC meet to set priorities, co-design activities, and track progress toward community goals, while also building civic awareness, leadership, and a stronger collective voice for Blue Island and Robbins. | Action Step 2: Establish a Stakeholder Volunteer and Ambassador Program that provides meaningful pathways for participation; such as event support, peer outreach, and advocacy. | Action Step 3: Expand BIRNN’s bilingual outreach by using social media, digital newsletters, and QR codes to share information and opportunities in English and Spanish, so more residents can stay informed and engaged. | Action Step 4: Strengthen Community Engagement through Emergency Rapid Response. Act as a liaison and coordinator of services and supports for Blue Island/Robbins residents who are impacted by emergencies (fires, flooding, immigration raids..etc) by connecting them to partner resources and providing limited direct relief when other options are unavailable. | Action Step 5. Host focused Lunch & Learn sessions and a community tour for business, foundation, and partner stakeholders to learn about BIRNN’s work, build relationships, and explore ways to support the network.
Activity | Hold hybrid meetings with RAC members, residents, and partners to name 3–5 community priorities and share a short summary within two weeks. Put these priorities into action through joint events (e.g., Safe Summer forum, resource fair, or project) to help prevent violence, connect families to resources, and build trust. Offer voter registration at BIRNN events and Community Conversations, and provide basic advocacy training (how to talk to public officials, speak in public, and share your story). Lift up resident and partner voices through newsletters, social media, and at least one public meeting, highlighting resident advocacy and connecting people to ongoing civic engagement opportunities. End the year with a reflection session to review what worked, set priorities for next year, and send out a one-page “Year in Review” (3–5 priorities, who’s responsible, and basic deadlines) within two weeks. | Develop a straightforward volunteer and ambassador framework with clearly defined roles, including event support, advocacy, and peer outreach. Recruit and onboard residents through Community Conversations, outreach initiatives, and partner referrals. Involve volunteers and ambassadors in at least one BIRNN event or outreach activity. | Enhance digital engagement with quarterly bilingual social media campaigns, a monthly e-newsletter, and QR codes in high-traffic community spots that link to BIRNN resources and programs. Track impact through likes, shares, follower growth, newsletter opens/clicks, and QR scans, and review these materials quarterly to improve clarity, reach, and bilingual, mobile-friendly access for residents. | BIRNN will use clear criteria and simple steps so help is fair and fast. Families must live in or be directly connected to Blue Island or Robbins, have an urgent short-term need (food, basic clothing, hygiene, immediate safety), and have already attempted to access other local resources (pantries, agencies, churches). A brief one-page intake form will be completed (name, contact, household size, need, and what was tried), and support will be modest and time-limited, with a simple cap per family per year. BIRNN staff will manage a small emergency pool (grocery cards, clothing support, hygiene kits), use the intake checklist to approve assistance, and coordinate with partners to confirm referrals and avoid duplication when possible. Each request will be logged (date, type of support, amount, referral source) so BIRNN can monitor use, identify trends, and adjust the safety-net fund over time. In addition, emergency response efforts will incorporate Know Your Rights education and connection to trusted community partners. BIRNN will collaborate closely with ICIRR and other local organizations to ensure that residents affected by emergencies—including fires, flooding, or immigration enforcement—receive accurate information about their rights and can access rapid community support. When relevant, families will be referred to KYR workshops, rapid response contacts, and partner-led advocacy resources to help strengthen safety, stability, and community resilience. | Stakeholder Lunch & Learns Host three in-person Lunch & Learn sessions a year for business, foundation, and partner stakeholders (about 12 people per session). Provide a simple meal and materials. Include a 10–15 minute presentation on BIRNN’s key initiatives (youth development, workforce, food security, health), followed by Q&A and discussion on how stakeholders can partner or support. Share a one-page handout with program highlights and ways to stay involved. Community Tour for Funders/Partners Host one guided community tour for foundations, potential funders, and private-sector partners. Visit key BIRNN sites to show programs in action and explain impact. Provide lunch and an informational packet summarizing BIRNN’s work and funding priorities. Collect brief feedback and document follow-up opportunities to strengthen relationships and support.
Resources | United Way Funding Support | United Way Funding Support | United Way Funding Support | Unrestricted Funds, United Way Funding Support | United Way Funding Support
Assignment | BIRNN Staff, RAC, Blue Island Park District, Robbins Park District, District 218, District 143.5, District 130, Blue Island Public Library, William Leonard Library, Southland Chamber of Commerce, Blue Island Chamber of Commerce, Local Leaders, Elected Officials, Faith-based partners (local churches in Blue Island and Robbins), ACCESS Healthcenter, Cook County Public Health. | BIRNN Staff, RAC, Sub-Commitee Members, Blue Island Park District, Robbins Park District, District 218, Blue Island Public Library, William Leonard Library, Southland Chamber of Commerce, Blue Island Chamber of Commerce | BIRNN Staff, RAC, Sub-Commitee Members, Partner Organizations, Blue Island-Robbins Municpalities | BIRNN, Illinois Coalition for Immigrant and Refugee Rights, Corazon a Corazon, Centro de Trabajadores Unidos, Local Faith Based partners, Blue Island Chamber of Commerce, Metropolitan Family Services | BIRNN Staff, Local Busineses, RAC, Community Members (Familiar and Unfamiliar wih the BIRNN)
Completion Date | Q3 Q4 | Q1 Q2 Q3 Q4 | Q1 Q2 Q3 Q4 | Q1 Q2 Q3 Q4 | Q4
Priority Ranking | 1 | 1 | 2 | 1 | 1
Improvement | BIRNN will strengthen community engagement and resident advocacy by aiming to have at least 70% of RAC members and partners join quarterly activities, Community Conversations, collaborative events, visibility efforts, voter registration, and basic advocacy training, so residents have regular opportunities to shape priorities and decisions. Year 1 will be a baseline year, with participation and feedback tracked (sign-ins, surveys, simple digital metrics) and shared back with the community to keep the work transparent, responsive, and community-driven. | The BIRNN will implement a resident volunteer and ambassador program designed to offer clearly defined pathways for engagement. Between five and ten residents shall serve as ambassadors, acquiring leadership experience, advocacy skills, and recognition, while simultaneously enhancing resident visibility, voice, and ownership in shaping network activities. | BIRNN will strengthen community engagement by consistently tracking digital outreach, monitoring social media analytics (likes, shares, comments, impressions, engagement rate), newsletter performance (open rates, click-throughs, interactions with content), and QR code scans/link usage, and logging all of these in a shared tracker or dashboard for quarterly review. By comparing this feedback and engagement data to goals and benchmarks, then adjusting content, format, and distribution methods (such as posting times, language, and media type) and sharing insights with staff and committee members, BIRNN will continually improve its campaigns and outreach strategies so more residents see, understand, and act on information and opportunities. | BIRNN builds trust and credibility, because families know there is a caring “last resort” when everything else has been tried. Fewer families fall through the cracks, as short-term crises (food, clothing, basics) are met quickly and with dignity. BIRNN strengthens connections with partners, using referrals and shared information to improve the overall safety net in Blue Island and Robbins. Data from the safety-net log helps BIRNN spot patterns and advocate for bigger solutions, guiding future programs and funding for community needs. | These Lunch & Learns and the community tour will strengthen BIRNN’s community engagement and sustainability by building stronger relationships with funders, businesses, and partners who better understand BIRNN’s work and community priorities. Stakeholders will leave with clear ways to support (funding, in-kind help, partnerships), while also hearing resident and RAC perspectives shared in the sessions. Over time, this increases BIRNN’s visibility, creates a warmer pipeline for resources, and ensures that community-driven needs are lifted up in conversations with decision-makers.
Updates | 6/18/2026 June RAC meeting was postponed due to inclement weather. Pending evalution outcomes for voter registration campaign that was coordinated in partnership with ICIRR. | I will be working with Sara to identify a volunteer coordinator to help organize and manage our volunteer program. This role will support the Stakeholder Volunteer and Ambassador Program by coordinating meaningful ways for stakeholders to participate, including event support, peer outreach, and advocacy | BIRNN has continued to expand its bilingual outreach through social media, digital communications, and other community-facing tools that share information in English and Spanish. This quarter, we continued to strengthen our approach to resident engagement and are working toward a more consistent process for tracking digital outreach, including social media engagement, newsletter activity, and QR code usage. These efforts are helping BIRNN improve access to information and build a stronger bilingual outreach strategy for the community. | Providing conitnued case management for families affected by Operation Midway Blitz. Hosted KYR Workshop on 2/6/25, 8 community members registered virtually, 7 attended in person. | BIRNN plans to host the first Stakeholder Lunch & Learn and a guided community tour in May for business, foundation, and partner stakeholders. The session will include a brief presentation on BIRNN’s key initiatives (youth development, workforce, food security, and health), time for Q&A and discussion, and a one-page handout with program highlights and clear ways to support. The May community tour will invite potential funders and partners to visit key BIRNN sites, meet partners and RAC voices, and see the work in action. We will provide lunch and an informational packet and will collect brief feedback and document follow-up opportunities to strengthen relationships and build a warmer pipeline of resources for BIRNN.
|  | Progress Update as of 6/18/26: BIRNN has started progress on Action Step 2 by developing a simple stakeholder volunteer and ambassador framework that will create meaningful ways for residents and community stakeholders to participate in the work of the network. The program will focus on clear roles such as event support, peer outreach, and advocacy, helping residents become more involved while building leadership experience and community ownership. Ken and Sara have worked together to identify a volunteer coordinator to help organize and manage this effort. Andrea Roberson has been identified and has agreed to support the volunteer and ambassador program. Her role will help strengthen coordination, communication, and follow-up with residents who are interested in serving as volunteers or ambassadors. Ken has also started developing tools to support the program, including volunteer and ambassador materials that will help track interest, define roles, and support onboarding. The current goal is to identify four resident ambassadors who can support BIRNN events, outreach activities, and community engagement efforts. Recruitment and identification of possible volunteers and ambassadors is currently in progress in coordination with Ms. Roberson. Volunteers and ambassadors may be involved in upcoming events and outreach opportunities, including Safe Summer, Robbins Rib Fest, and Robbins Festival Weekend. These steps will help BIRNN create a more organized and meaningful pathway for residents to participate, support events, share information with peers, and help advocate for community needs. Over time, this program will strengthen resident voice, visibility, leadership, and ownership in BIRNN’s work. | Progress Update as of 6/18/26: BIRNN has continued making progress on Action Step 3 by expanding bilingual outreach through social media, digital newsletters, flyers, partner sites, the website, and other community-facing communication tools. BIRNN has started sharing information in both English and Spanish to help more residents stay informed about programs, resources, events, and opportunities. Sara is assisting with Spanish translation and review to help ensure outreach materials are clear, accurate, and accessible for Spanish-speaking residents. BIRNN is also continuing to use its monthly e-newsletter as part of its communication strategy, along with social media, email, flyers, partner announcements, and website updates. Ken has drafted a bilingual outreach process and is working on a form to track digital outreach efforts, including social media engagement, newsletter activity, QR code usage, and other communication efforts. This form will help BIRNN begin tracking likes, shares, comments, follower growth, newsletter opens and clicks, QR scans, and other measures that show how residents are engaging with information. QR codes are still in development and will be used to help connect residents to BIRNN resources, programs, and updates in a more mobile-friendly way. BIRNN also plans to begin adding a blog to the website in July, which Ken will help start, to share regular updates, stories, resources, and community information. Bilingual outreach will be used for upcoming community events, including Safe Summer, Robbins Rib Fest, and Robbins Festival Weekend. These efforts will help BIRNN strengthen communication, improve access to information, and build a more consistent bilingual outreach system for residents in Blue Island and Robbins. | Progress Update as of 6/18/26: BIRNN has continued to strengthen community engagement through emergency rapid response by using its partner network to respond quickly when residents and families are impacted by crisis situations. This includes emergencies such as fires, flooding, immigration enforcement, and other urgent needs that affect Blue Island and Robbins residents. BIRNN continues to share timely and accurate information through trusted communication channels and connect residents to resources such as food access, legal aid, behavioral health services, and other emergency supports. The team is also coordinating directly with partner organizations to help streamline referrals, avoid duplication when possible, and make sure families are connected to the right resources. Ken has created a draft one-page intake form to help guide emergency response requests. The form will help document basic information such as household size, type of need, referral source, support provided, and follow-up needed. This will help BIRNN respond in a fair and organized way while also tracking trends and gaps over time. A small emergency support pool has been created, and BIRNN is continuing to add to it with the assistance of partner organizations, county resources, and United Way resources. This support may include grocery cards, clothing support, hygiene items, and other limited direct relief when other options are not immediately available. BIRNN is also continuing to work with partner organizations to provide case management and support for families affected by Operation Midway Blitz. One family was connected to mutual aid funds for travel support to reunite with their father after deportation. BIRNN also hosted a Know Your Rights workshop on 2/6/25. Eight community members registered virtually, and seven attended in person. This effort helped connect residents to important information about their rights and available community supports. As of 6/18/26, BIRNN began coordinating with the Public Defender’s Office at the Markham Courthouse to support clients of the Public Defender who may be detained by ICE at or near the courthouse. BIRNN is also providing program referrals to Centro de Trabajadores Unidos and Beyond Legal Aid. These efforts are helping BIRNN build a more organized rapid response process that connects residents to emergency support, trusted partners, legal resources, and follow-up services when urgent needs arise. | Progress Update as of 6/18/26: BIRNN has continued planning for Action Step 5 by preparing to host focused Lunch & Learn sessions and community tours for business, foundation, and partner stakeholders. The first Lunch & Learn and community tour were originally planned for May but have been moved to September so BIRNN can incorporate 2027 planning and use the opportunity to solicit assistance and support from business, foundation, and partner stakeholders. Ken has created draft planning materials to support this effort, including a draft Lunch & Learn agenda, one-page handout, invite list, tour outline, feedback form, and informational packet. These materials will help BIRNN present its key initiatives, explain funding and partnership priorities, and give stakeholders clear ways to support the network. The September Lunch & Learn will focus on helping stakeholders learn more about BIRNN’s work in food insecurity, youth development, workforce development, and health. The session will include a short presentation, time for questions and discussion, and opportunities for stakeholders to explore ways they can support through funding, in-kind help, partnerships, and shared resources. The Lunch & Learn and community tours will be separate activities. Community tours will be discussed further as part of the planning process. Ken has already brought two potential funders out to see BIRNN’s work and community needs firsthand, but BIRNN has not yet hosted a group tour. BIRNN will continue identifying individuals and potential funders to tour the community and learn more about the work happening in Blue Island and Robbins. Potential attendees and stakeholders have already been identified, including business, foundation, United Way, and partner connections. RAC and community voices will also be included so stakeholders hear directly from residents and partners about community priorities, needs, and opportunities for support. This plan will be reviewed during the August workplanning meetings before the September Lunch & Learn. These steps will help BIRNN build stronger relationships, increase visibility, create a warmer pipeline for resources, and connect future support to community-driven needs.

## Programming
Neighborhood Network Action Plan
Programming | Goal: Build resident power in Blue Island and Robbins by offering programs that strengthen economic opportunities, health and wellness, social-emotional wellbeing, and civic engagement, so families and communities can shape and sustain their own future.
| Action Step 1: Strengthen Emotional Wellness and Community Leadership | Action Step 2: Advance community wellness and food security through community-hosted health initiatives (such as family fitness events, nutrition classes, and resource fairs), and separately provide subgrants to Blue Cap Pantry and the Robbins Mobile Market to run nutrition workshops and conduct community surveys on food insecurity and related needs in Blue Island and Robbins | Action Step 3:Strengthen Financial Health and Economic Mobility in partnership with local colleges, unions, and workforce agencies. | Action Step 4: Provide a subgrant to the Robbins Eagles organization to run a January through December Youth Development Track focused on leadership and enrichment for local youth. | Action Step 5. Launch an 8-week Nonprofit Bootcamp that walks participants from idea to launch, covering basics like governance, financial basics, fundraising, and program planning, with bilingual materials, office hours, and a 90-day follow-up to support next steps. BIRNN will also award two small subgrants to Bootcamp participants who plan to operate their nonprofit projects in Blue Island or Robbins. | Action Step 6: Provide a subgrant to HOPE Center to offer monthly, hands-on gardening classes, including basic hydroponics, that help families grow their own food at home and on-site, strengthening food security in Blue Island and Robbins. | Action Step 7: Community Partner Subgrant Programming
Activity | Foster emotional resilience and deepen community bonds by co-coordinating monthly bilingual workshops that address stress management, conflict resolution, civic engagement, and advocacy. In addition, establish a bi-weekly support group to support community members experiencing emotional strain tied to federal policy shifts. Local experts, partner agencies, and community leaders will facilitate these sessions to empower residents with tools for leadership and advocacy. | Activities – Community-Hosted Health Initiatives Host seasonal family fitness events in Blue Island and Robbins (family walks, games, movement days). • Organize community health and resource fairs with partners that offer basic health screenings, mental health and wellness information, and connections to food, housing, and workforce resources. • Provide health and wellness presentations (e.g., managing stress, healthy habits for families) at community sites to support long-term wellness and stronger connections to local services. Activities – Subgrants to Blue Cap Pantry & Robbins Mobile Market • Run regular nutrition workshops at pantry/mobile market sites, focused on affordable healthy eating, label reading, and simple meal planning. • Conduct short community surveys (paper or QR) during pantry/mobile market days to learn about food insecurity and other basic needs. • Connect clients to additional resources (BIRNN programs, benefits screening, health services) using simple referral cards or a resource board at each site. • Track attendance and survey results in a simple log and share a brief summary and key themes with BIRNN each quarter to inform future programs and funding. | Enhance financial stability and workforce readiness through accessible financial education and reentry support. Host quarterly financial literacy workshops and employment resource events in partnership with local colleges, unions, and workforce agencies. Programming will include financial coaching, credit-building sessions, tattoo removal opportunities, and guidance on reentry and career advancement. | We will work with the Robbins Eagles organization to design and run a year-round Youth Development Track that offers bi-monthly sessions on life skills, leadership, tutoring/enrichment, and service learning. Together, we will build: (1) Leadership & life skills workshops to strengthen communication, problem-solving, and decision-making; (2) Academic enrichment and tutoring in core subjects plus STEM or financial literacy; (3) Service learning and civic engagement through at least two community projects and partner-led sessions; and (4) Family engagement through monthly updates, two family nights, and chances for families to join youth learning and service activities, including youth showcases to celebrate growth. | Bootcamp Activities (8 Weeks) Intro: clarify your “why,” who you serve, and your nonprofit name. Market research: scan community needs, competition, and what makes your nonprofit unique. Mission & vision: write clear statements and define desired community impact. Nonprofit setup: boards, incorporation, bylaws, and basic tax-exempt concepts. Planning: create a simple business/work plan with SMART goals. Money: basics of fundraising, donors, and finding/applying for grants. Marketing: outreach using social media, print, and partnerships. Wrap-up: review resources, support options, and next action steps. | Host four quarterly, hands-on gardening classes on topics like soil prep, raised beds/containers, basic hydroponics, seed starting, pest control, harvesting, and simple cooking demos using garden produce. BIRNN will support HOPE Center to set up and maintain garden spaces, including two garden build days to install or refresh beds and compost areas. Provide spring and fall seedling and supply distributions so households can start or expand home gardens. Offer short nutrition tastings with easy recipes at harvest times to connect gardening to healthy eating. Promote opportunities through flyers, partner sites, and social media posts to reach Blue Island and Robbins residents. | Support and expand high-quality, community-centered programming by awarding subgrants to local partner organizations that align with BIRNN’s priority areas (education, financial health, healthy eating, socio-emotional wellness, rapid response, and family stability). BIRNN will award subgrants to community partners to implement programs that directly support network priority areas: family stability, financial health, education, socio-emotional wellness, and rapid response. Metrics: At least 4–6 community partners will receive funding, with each subgrantee required to report on program outputs (e.g., number of participants served, workshops completed) and outcomes (e.g., increased access to resources, improved skills, reduced barriers). BIRNN will provide technical assistance, clear application guidelines, and supportive monitoring to ensure partners, especially small grassroots groups can successfully design and implement programs. The subgrant initiative strengthens BIRNN’s role as a hub for community collaboration and expands programming that addresses urgent needs in Blue Island and Robbins.
Resources | United Way Funding Support | United Way Funding Support | United Way Funding Support | United Way Funding Support | United Way Funding Support | United Way Funding Support | United Way Funding Support
Assignment | Metropolitan Family Services, Crisis Center for South Suburbia, Sertoma Star Center, Solid Ground Behavioral Health Services, Cook County Health – Behavioral Health Team, District 143.5, District 130, District 218, Corazón a Corazón,YWCA Metropolitan Chicago, Moraine Valley Community College, Credit Union1, T Hill Consultant LLC, Riveredge Hospital, HOPE Center, First Evangelical Lutheran Church, Center for Self Actualization | Metropolitan Family Services, Moraine Valley Community College, District 143.5, District 130, District 218, YWCA Metropolitan Chicago, United Way of Metro Chicago,Credit Union 1, BlueCap, Sertoma Star Services, T Hill Consultant LLC, Riveredge Hospital, HOPE Center, First Evangelical Lutheran Church, Northwestern Medicine, Robbins and Blue Island Park District | Metropolitan Family Services, Moraine Valley Community College, District 143.5, District 130, District 218, YWCA Metropolitan Chicago, United Way of Metro Chicago,Credit Union 1, Illinois Department of Employment Security, BlueCap, Sertoma Star Services, T Hill Consultant LLC, Riveredge Hospital, HOPE Center, First Evangelical Lutheran Church, Northwestern Medicine, Moraine Valley Community College | Robbins Eagles Organization, BIRNN Staff, Blue Island-Robbins Park Districts, The Rita Center, Cease Fire, School Districts 130, 143.5 Corazón a Corazón, Robbins-Blue Island Libraries | BIRRN Staff, Probono Facilatators from Cook County, United Way, Some Paid Facilatators When Needed and nonprofits leaders | Hope Center Staff, Community Volunteers, Partner Organizations, RAC, Robbins Park District, Blue Island Park District, Blue Island Forestry Board | BIRNN Network Partners
Completion Date | Q1 Q2 Q3 Q4 | Q1 Q2 Q3 Q4 | Q4 | Q1 Q2 Q3 Q4 | Q4 | Q3 Q4 | Q2Q3Q4
Priority Ranking | 1 | 2 | 2 | 1 | 2 | 2 | 2
Improvement | 12 monthly leadership and wellness workshops. Sessions will include interactive learning, peer-led discussions. Participant sign-ins, agendas, and feedback summaries will be used to measure engagement levels, knowledge gained, and overall impact of the workshops on participants’ leadership skills and emotional wellbeing. | These efforts will improve life in Blue Island and Robbins by giving families more chances to move, connect, and get support around health and food. Community-hosted events will help residents learn about local resources, build healthy habits, and feel more connected to each other and to BIRNN. At the same time, the subgrants to Blue Cap Pantry and the Robbins Mobile Market will deepen support where families already go for help, adding nutrition education, referrals, and simple surveys that lift up community voice. Together, this will lead to better access to healthy food, stronger wellness practices, and clearer data to shape future programs and funding. | Conduct three quarterly financial literacy workshops and two employment resource events, engaging at least 60 residents annually. Provide individual financial coaching and reentry support (tattoo removal, expungement, job readiness) in partnership with local organizations. Track participation and outcomes through attendance logs, pre/post assessments, and referral follow-ups. Maintain partner agreements and impact summaries documenting collaboration, outcomes, and participant success stories. Submit an end-of-year report detailing measurable results, including credit, employment, and reentry progress. | This Youth Development Program will strengthen the Eagles’ youth arm by turning it into a consistent, year-round experience where young people build life skills, leadership, academics, and a habit of giving back—not just playing sports. With a simple curriculum, regular check-ins on attendance and progress, partner-led activities, and family nights, it also creates a stronger, more sustainable structure for growing future youth leaders for both the Eagles program and the wider Blue Island–Robbins community. | The Bootcamp will build local capacity in Blue Island and Robbins by helping residents launch and strengthen nonprofits that understand and address community needs, resulting over time in more homegrown organizations providing services, advocacy, and support tailored to the issues our neighborhoods face. | Families in Blue Island and Robbins gain practical skills to grow their own food, leading to more home gardens and fresh produce at home. Food insecurity is reduced over time as households have another source of fruits and vegetables, especially in warmer months. Residents build stronger habits around healthy eating, by connecting gardening with simple recipes and tastings. HOPE Center and BIRNN strengthen their role as community hubs, creating ongoing engagement with families through garden classes, build days, and seasonal distributions. | BIRNN will award 3-4 subgrants to community partner organizations aligned with the network’s priority areas (education, financial health, healthy eating, socio-emotional wellness, rapid response, and family stability). BIRNN will provide a plain-language application, bilingual materials, pre-application info sessions, and 1:1 technical assistance. Subgrantees will receive a standardized reporting template, quarterly check-ins, and opportunities to participate in partner learning roundtables. At least 90% of funded partners will submit complete program reports demonstrating measurable impact, such as increased access to essential resources, improved skills, or reduced barriers for Blue Island and Robbins residents.
Updates | Collab planning with BIPL for Children's Day Celebration on 5/2/26 |  | On March 17, 2026, BIRNN met with Wintrust to explore opportunities for collaboration around financial literacy programming. On March 20, 2026, the Blue Island Robbins Neighborhood Network, in partnership with the Village of Robbins, will host a Job Fair aimed at connecting residents to employment opportunities and workforce resources.
| Launch date for Grief Support Groups on 3/26/26 and monthly workshops will be led by Cook County Behavioral Health Department. BIRNN will support in marketing, etc. | Spring Into Wellness Fair scheduled for 05/16/2026. | Community High School District 218 Job Fair on 3/7/26 at the CHSD 218 Administrative Building in Oak Lawn. BIRNN will support in outreach | I met with the Robbins Eagles leadership to discuss the Youth Development Track and the life skills workshops that will be offered as part of the January–December leadership and enrichment programming. We will be meeting again to confirm deliverables, clarify expectations, and finalize the scope of work. | We will begin the cohort in April. We have already spoken with County partners about facilitating some of the workshops, and we are also coordinating with our MFS family to support delivery. The plan will include speaker/facilitator support for outside presenters, as well as materials and snacks to support participant engagement throughout the cohort. | We met with Pastor Moy to discuss the subgrant and confirm what program it will support, including monthly, hands-on gardening classes with basic hydroponics to strengthen food security in Blue Island and Robbins. We also received copies of subgrant agreements that have been used with our BPNC family. Next, we will make the necessary adjustments and prepare a draft agreement for approval. Once the draft is ready, we will meet again with Pastor Moy to review deliverables and finalize and sign the agreement. | We are currently working to provide subgrants to Blue Cap and the Robbins Mobile Market to support community partner programming and strengthen our efforts around food access and basic needs in Blue Island and Robbins.
| High School Voter Registration on 2/28/26 at Eisenhower High School in collaboration with ICIRR. | 3/31/26 Colorectal Cancer Screening Presentation in collaboration with the American Cancer Society and the HOPE Center. | Youth Opportunities Fair hosted by Congresswoman Robin Kelly on 2/22/26 to connect youth and families with summer employment, internships, and career pathway programs. BIRNN will support outreach and share with partners, schools, and residents to increase access to youth workforce and enrichment opportunities. | Subgrant contracts have been developed and shared with the Steering Committee for review to ensure alignment with BIRNN priorities, compliance requirements, and partner capacity prior to finalization and implementation. |  | Subgrant contracts have been developed and shared with the Steering Committee for review to ensure alignment with BIRNN priorities, compliance requirements, and partner capacity prior to finalization and implementation. | Subgrant contracts have been developed and shared with the Steering Committee for review to ensure alignment with BIRNN priorities, compliance requirements, and partner capacity prior to finalization and implementation.
| Illinois Family Roots Pilot Program, an initiative that provides residents of African descent with access to genealogical research and DNA analysis to help reconnect individuals and families with their ancestral heritage. Event is hosted at BIPL on 2/21/26 | Continue planning for the Spring Into Wellness Fair scheduled for May 16, 2026, with key components already confirmed. A youth soccer clinic and a vaccination clinic in partnership with the Cook County Department of Public Health have been secured. Outreach to support event resources is also underway, including requests for food donations from Kroger, Target, and Restaurant Depot. Additional partners and activities continue to be coordinated to ensure a well-rounded, accessible event for the community. | 6/18/2026: Began developing the Second Chance Business Academy, a reentry program designed to support returning residents with the skills, resources, mentorship, and guidance needed to start a small business, side hustle, or self-employment opportunity. | Progress Update as of 6/18/26: BIRNN has made strong progress on Action Step 4 by moving the Robbins Eagles Youth Development Track from planning into implementation. The subgrant has been reviewed and signed by both parties, which allows the program to move forward with clear expectations, deliverables, and tracking requirements. Ken met with Robbins Eagles leadership to discuss the youth development program, which is now called Beyond the Game. The program will focus on helping youth build leadership, life skills, academic confidence, service learning, and a stronger connection to the broader Blue Island and Robbins communities. Rio and Charlotte have been identified as the adult leaders for the program. Youth recruitment is currently underway, and the program has already completed one volunteer event and held its first workshop. The workshop topics will include leadership, communication, decision-making, conflict resolution, financial literacy, tutoring and enrichment, service learning, and family engagement. Ken has also created a monthly report that will be used to track program activities, attendance, progress, outcomes, family engagement, and volunteer or service-learning efforts. This report will help BIRNN and the Robbins Eagles stay aligned, monitor progress, and document the impact of the Beyond the Game program throughout the year. These steps are helping strengthen the Robbins Eagles’ youth development work by creating a consistent program that goes beyond sports. Over time, Beyond the Game will help local youth build leadership skills, give back to the community, and grow as future leaders in Robbins and the broader Blue Island and Robbins communities. | Progress Update as of 6/18/26: BIRNN has continued planning for Action Step 5 by developing the structure for an 8-week Nonprofit Bootcamp that will help residents move from idea to launch. The Bootcamp will support participants in learning the basics of starting and strengthening a nonprofit, including governance, financial basics, fundraising, program planning, marketing, and community impact. The Bootcamp is tentatively scheduled to begin on Tuesday, September 8, and will meet in person each Tuesday evening for eight weeks. The September timeline will allow BIRNN to build a stronger cohort, confirm facilitators, finalize the workshop topics, and align the Bootcamp with 2027 planning and community priorities. Planning is currently underway through bi-monthly planning sessions led by Ken, Dr. Powell, and Lina Shepard. Ken has created a draft flyer and a draft outline of topics for each of the eight weeks. The weekly topics will include clarifying the nonprofit’s purpose, understanding community needs, writing mission and vision statements, learning nonprofit setup basics, creating a simple work plan, understanding fundraising and grants, developing outreach strategies, and identifying next steps after the Bootcamp. BIRNN is still deciding on workshop presenters and will reach out to County partners in late July to explore possible facilitation support for some of the sessions. The Bootcamp will be offered in English, and the resources will include speaker and facilitator costs for outside presenters, as well as materials and snacks to support participant engagement throughout the cohort. Recruitment will begin in August, with a focus on residents of Blue Island and Robbins who have nonprofit ideas connected to community needs. BIRNN will also award two small subgrants to Bootcamp participants at the end of the Bootcamp. The subgrant amounts have not yet been finalized. These steps are helping BIRNN build local capacity by creating a practical pathway for residents to develop nonprofit ideas, strengthen leadership skills, and launch or grow projects that serve Blue Island and Robbins. | Progress Update as of 6/18/26: BIRNN has made progress on Action Step 6 by moving the HOPE Center gardening subgrant from planning into implementation. The subgrant agreement has been reviewed and signed, allowing the program to move forward with clear expectations and deliverables. BIRNN met with Pastor Moy to discuss the program and confirm that the subgrant will support monthly, hands-on gardening classes, including basic hydroponics. These classes are ongoing and are designed to help families in Blue Island and Robbins learn practical skills for growing food at home and on-site. The garden space is already in place, and seedling and supply distributions have also started. These efforts help residents build or expand home gardens while increasing access to fresh produce and supporting stronger food security in the community. Ken has created a monthly report that will be used to track class activities, attendance, topics covered, supplies distributed, participant feedback, and outcomes. Ken has reached out to Pastor Moy a couple of times and is waiting for his approval of the monthly reporting process. This work is helping BIRNN and HOPE Center strengthen their role as community hubs for food access, gardening education, and healthy living. Over time, the program will help families gain gardening skills, increase access to fresh food, and support food security in Blue Island and Robbins. | Progress Update as of 6/18/26: BIRNN has continued making progress on Action Step 7 by moving forward with community partner subgrants that support high-quality, community-centered programming in Blue Island and Robbins. Four subgrants have been agreed upon to support work connected to BIRNN’s priority areas, including education, financial health, healthy eating, socio-emotional wellness, rapid response, and family stability. The Blue Cap subgrant has been reviewed and signed. BIRNN is also still waiting for the agreement with Catholic Charities and the Robbins Park District to be signed so the Robbins Mobile Market can begin. The Robbins Park District has made several attempts to reach Catholic Charities through written communication and phone calls to move the agreement forward. Subgrant materials have been sent to the Steering Committee for review to ensure alignment with BIRNN priorities, compliance requirements, and partner capacity. Ken has also created a monthly report for all subgrantees to use in tracking program activities, number of participants served, workshops or services completed, outcomes, barriers reduced, and follow-up needs. BIRNN will provide technical assistance to subgrantees to help with reporting, compliance, documentation, and program implementation. This includes plain-language guidance, support with monthly reports, check-ins as needed, and help making sure partners understand expectations. BIRNN will also continue working to make materials clear and accessible, including bilingual support when needed. These subgrants will help expand community-centered programming and strengthen the role of local partners in addressing urgent needs in Blue Island and Robbins. This work also helps BIRNN continue serving as a hub for collaboration, shared resources, and partner-led solutions that support residents and families.
| Advance Legal Planning workshops hosted by the Center for Disability & Elder Law on 3/2/26 at William Leonard Public Library (Robbins) and 3/3/26 at Blue Island Public Library. Workshops will cover Transfer on Death Instruments (TODI), wills, and powers of attorney. BIRNN will support in marketing and connecting residents to legal planning resources. | 6/18/2026 Spring Into Wellness Fair, low attendance due to inclement weather and extreme heat. Had over 30+ vendors in attendance. |  |  |  |  | Progress Update as of 6/18/26: BIRNN has continued making progress on Action Step 7 by moving forward with community partner subgrants that support high-quality, community-centered programming in Blue Island and Robbins. Four subgrants have been agreed upon to support work connected to BIRNN’s priority areas, including education, financial health, healthy eating, socio-emotional wellness, rapid response, and family stability. The Blue Cap subgrant has been reviewed and signed. BIRNN is also still waiting for the agreement with Catholic Charities and the Robbins Park District to be signed so the Robbins Mobile Market can begin. The Robbins Park District has made several attempts to reach Catholic Charities through written communication and phone calls to move the agreement forward. Subgrant materials have been sent to the Steering Committee for review to ensure alignment with BIRNN priorities, compliance requirements, and partner capacity. Ken has also created a monthly report for all subgrantees to use in tracking program activities, number of participants served, workshops or services completed, outcomes, barriers reduced, and follow-up needs. BIRNN will provide technical assistance to subgrantees to help with reporting, compliance, documentation, and program implementation. This includes plain-language guidance, support with monthly reports, check-ins as needed, and help making sure partners understand expectations. BIRNN will also continue working to make materials clear and accessible, including bilingual support when needed. These subgrants will help expand community-centered programming and strengthen the role of local partners in addressing urgent needs in Blue Island and Robbins. This work also helps BIRNN continue serving as a hub for collaboration, shared resources, and partner-led solutions that support residents and families.
041826: Officially launched a bi-weekly grief support group as part of its Emotional Wellness efforts. The group has met twice to date, with an average of four participants per session. While attendance remains low, outreach efforts are ongoing, and BIRNN plans to assess community barriers to participation
6/18/2026 Hosting Yoga on the Farm at the HOPE Center on 6/29/26 in partnership with MFS Community Schools and The Center for Self Actualization
Note on J6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Should have a joint focus